## Slide 1: Mission Science lessons learned Flight
Should be able to switch Ku coverage in flight – Dave F.
Scientists need to keep a close eye on cloud top height – should make sure we’re using solid algorithms
Hope to relax close vetting of dropsonde patterns from NY center – Phil H
Nose camera needs to be upgraded, and should be in MTS + stormscope, images need to be saved. – Dave F.
HD-vis needs to be properly pre-flighted to prevent frost on lens. Heater tape does not work.
Relax constraint on CPL operation over land when we are higher than FL550 – Phil H
For transits, early AM takeoff to avoid afternoon monsoon weather development in SW US – need to check SW US Wx
Should try and optimize our time over storms during daylight hours in order to use satellite visible imagery – better situational awareness. This would generally require a night take-off. – Phil H

## Slide 2: Mission Science lessons learned General
Chase adds an extra level of complexity. We need to open up flexibility by doing night operations. – Phil H
Need to relax the restricted flight areas in order to more quickly fly towards targets (less time ascending to altitude) . – Phil H
VACAPES restrictions almost caused a flight cancellation. Can we get a more open system for flying? – Phil H

## Slide 3: Mission Science lessons learned PMOF & MTS
Wall clocks in PMOF need to be synchronized – Dave F.
Plots on MTS need time stamps that show the valid times for the products. – Aaron D.

## Slide 4: Mission Science lessons learned Mission Science (1)
Need some pre-flight discussion amongst mission scientists to discuss in-flight contingency plans (e.g., AVAPS fail, ATC issues, high cloud diverts, etc.) – Scott & Paul
2 mission scientists need to be on duty so one can go back to the hangar and work on revising flight tracks, bathroom & food breaks
Need better discussion of items to be included in mission science flight log (report). - Paul
Have a mission scientist “book” at the mission scientist station
  Need to post key phone numbers prominently at the Mission Scientist station (Paul, Scott, etc.)
  We need an "pilot weather" print out prepared before each flight for temp & winds at flight altitude – include in mission scientist book
  A protocol needs to be in place for whom the Mission Scientist should call in case of flight revisions
  Need clearer rules regarding when to make flight track revisions (aggressive vs conservative)
  Need email list for emailing new flight coordinates (who should get it and who should not get it)
  Email lists need to be tested (HS3 listserve has not been exceptionally reliable)

## Slide 5: Mission Science lessons learned Mission Science (2)
A person able to make revised flight tracks need to be on duty at all times during flights to determine new points and post the new track in Mission Tools
Information flow between mission scientists and pilots is sub-par
  We need real-time screen-sharing (e.g., WebEx) between PMOF, flight planners/forecasters, and pilots
Need to be prepared to act quickly with sufficient lead time for pilots to re-file. (Today the pilots needed to re-file 40 min in advance of the diversion.)
Needs to be understood that Mission Scientists are not “forecasters.” We are assessing situations based on old information.
Given the opportunity to circumnavigate the core of a storm several times, depending on the latency of sonde data in MTS, one should check to see where data has dropped out for choosing future drop locations

## Slide 6: Flight Planning Lessons
The workflow time line between 8:00 AM WX brief and 10:00 AM deadline needs improvement
We need better automated tools for dropsonde placement – Leslie L
We should train more forecasters & mission scientists in using the flight planning software – Leslie L
While a flight is in progress, we should not forget that we need to plan flights for the following days (this is particularly true when we have both AV-1 and AV-6 at WFF)
It would be useful to have a line-transit-time estimator tool in MTS – Aaron D.